## Project Planner
Victorian Accident Analysis Project
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1.0/1 Planning/Project Plan | 1 | 3 | 1 | 3 | 100%
1.1.1 Introduction | 1 | 0.5 | 1 | 0.5 | 100%
1.1.2 WBS | 2 | 1 | 2 | 1 | 100%
1.1.3 Activity Definition | 3 | 1 | 3 | 1 | 100%
1.1.4 Gantt Chart | 3 | 0.5 | 3 | 0.5 | 100%
2.0 Documentation | 4 | 7 | 4 | 7 | 100%
2.1 Software Design Document | 4 | 5 | 4 | 5 | 100%
2.1.1 System Vision Document | 4 | 1 | 4 | 1 | 100%
2.1.2 Software Requirements | 5 | 1 | 5 | 1 | 100%
2.1.3 Use Cases | 6 | 1 | 6 | 1 | 100%
2.1.4 Software Components and Design | 7 | 1 | 7 | 1 | 100%
2.1.5 Interface Design | 8 | 1 | 8 | 1 | 100%
2.2 Software Testing Report | 27 | 1 |  |  | 0%
2.3 Executive Summary | 28 | 1 |  |  | 0%
3.0/1 Production/Develop Project | 10 | 15 |  |  | 0%
3.1.1 Functional Requirements | 10 | 11 |  |  | 0%
3.1.2 Visual Requirements | 21 | 4 |  |  | 0%
4.0/1 Testing | 25 | 3 |  |  | 0%
Activity 19 |  |  |  |  | 0%
Activity 20 |  |  |  |  | 0%
Activity 21 |  |  |  |  | 0%
Activity 22 |  |  |  |  | 0%
Activity 23 |  |  |  |  | 0%
Activity 24 |  |  |  |  | 0%
Activity 25 |  |  |  |  | 0%
Activity 26 |  |  |  |  | 0%
Activity 27 |  |  |  |  | 0%
Activity 28 |  |  |  |  | 0%
Activity 29 |  |  |  |  | 0%
Activity 30 |  |  |  |  | 0%
Activity 31 |  |  |  |  | 0%
Activity 32 |  |  |  |  | 0%
Activity 33 |  |  |  |  | 0%
Activity 34 |  |  |  |  | 0%
Activity 35 |  |  |  |  | 0%